**DETAIL OF LAND ACQUISITION CASES DISTRICT RAHIM YAR KHAN**

|  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sr. No** | **Name of project** | **Acquiring Agency** | **No. of Mouzas under Acquisition** | **Date of Notification u/s 4(1)** | **DPAC meeting** | **Fund Deposited** | **Date of Notification u/s 17(4) & 6 of 5** | **Remarks** |
| 1 | NHA/  Dual carriage way | NHA | Liaquatpur (19) | Notified | Done | - | - | NHA has constructed road long ago and after that process was started for acquisition of land by the NHA, but due to wrong working by the then LAC, NHA i.e. alignment / actual survey and non availability of funds, further process is not being carried out.  The Deputy Commissioner R.Y.Khan has constituted team under the Chairmanship of concerned Assistant Commissioners vide minutes of meeting dated 15.09.2017 to check the anomalies .  Furthermore, In the year 2019 BOR appointed Assistant Commissioner, Rahimyarkhan & Sadiqabad as LACs for DCW and ACW projects respectively. |
| Khanpur (07) | Notified | Done | - | - |
| R.Y.Khan  (08) | Notified | Done | - | - |
| NHA/  Additional carriage way | Sadiqabad  (01) | Notified | Done | - | - |
| 2 | Nishtar Ghaat Bridge Package-I) Construction of road by NHA of SBBBP | NHA | Khanpur  (07) | Notified  (04) | Done | Deposited | - | * AS per directions of BOR dated 07-04-2021 rates were rationalized by reconvening meeting of DPAC on 10-06-2021. Case is now forwarded to the Assistant Commissioner, Khanpur as well as the LAC appointed by BOR/Tehsildar Khanpur, Mr. Muhammad Junaid Khan for re-submitting it as per rationalized rates by DPAC dated 10-06-2021. * NHA has not completed survey reports due to Indus River of remaining 03 Mouzas. |
| **Sr. No** | **Name of project** | **Acquiring Agency** | **No. of Mouzas under Acquisition** | **Date of Notification u/s 4(1)** | **DPAC meeting** | **Fund Deposited** | **Date of Notification u/s 17(4) & 6 of 5** | **Remarks** |
| 3 | I-Irrigation Department for extension of Minchin Flood Bund | Irrigation | RY khan (09) | Notified | Done | Deposited | - | Concerned Assistant Commissioners are working as LACs of this project. Approval of cost of land is underway from the authority concerned. |
| Sadiqabad  (02) | Notified | Done | Deposited | - |
| II-Irrigation Department for extension of Minchin Flood Bund  (Seepage Drain) | Liaquatpur  (32) | Notified | Done | Deposited | - | Due to alignment issues and litigation pending adjudication in the Honorable Lahore High Court Bahawalpur Bench Bahawalpur, award of 15 Mouzas/Chaks have been announced but award of remaining is pending due to some technical reasons and wrong taking over of possession. |
| 4 | Pak Army through Military Estate Officer Hyderabad circle Hyderabad  (Extension of Cantonemnet) | Military Estate Officer Hyderabad. | R.Y.Khan (01) | Notified | Done | Deposited | - | * Assistant Commissioner, R.Y.Khan is working as LAC of this project. * Approval of cost received from the authority has already been conveyed to the AC/ LAC, R.Y.Khan. * Award process is being carried out by the AC/LAC, RYK. |
| Pak Navy through its HQ Lahore for acquisition of land for PN recruitment centre at RYK. | Military Estate Officer Hyderabad. | R.Y.Khan (01) | Notified | Done | Deposited | - | Case is under process. Section 5 notified. Objections u/s 5-A is being heard by the Assistant Commissioner/ Land Acquisition Collector, Rahimyarkhan. |
| 5 | Provincial Highway Department –Acquisition of land for Construction of Flyover | Provincial Highway | Khanpur  (01) | Notified | Done | Deposited | - | * Land Acquisition Collector, Provincial Highway Multan is working as LAC of this project. * Directions received by Commissioner BWP for re-assessing rates of all category of land. After doing the need full, case was re-submitted to the Commissioner, Bahawalpur for approval & publication of notification u/s 17(4) & 6 in the Punjab Gazette. |
| **Sr. No** | **Name of project** | **Acquiring Agency** | **No. of Mouzas under Acquisition** | **Date of Notification u/s 4(1)** | **DPAC meeting** | **Fund Deposited** | **Date of Notification u/s 17(4) & 6 of 5** | **Remarks** |
| 6 | Provincial Highway Department –Acquisition of land for Construction of road leading to Ch. Sugar Mills | Provincial Highway | Khanpur (05) | Notified | Done | Deposited | - | * Land Acquisition Collector, Provincial Highway Multan is working as LAC of this project. * Case is being processed u/s 5 of Land Acquisition Act, 1894. |
| 7 | Sui Northern Gas Pipe Lines Limited | SNGPL | R.Y.Khan  (24 | Notified | Done | Deposited | - | * Land Acquisition Collector, SNGPL Lahore is working as LAC of this project. * Case is being processed u/s 5 of Land Acquisition Act, 1894. |
| SNGPL | LQP  (09 | Notified | Nil | Not deposited | - | * Land Acquisition Collector, SNGPL Lahore is working as LAC of this project. * Case is being processed for assessment of cost of land and reports regarding Market price on Performa devised by this office is being called from concerned tehsils except tehsil Khanpur which is awaited. |
| SNGPL | KPR  (10) | Notified | Nil | Not deposited | - |
| SNGPL | SDK  (23) | Notified | Nil | Not deposited | - |
| 8 | Public Health Engineering Department. | PHE | R.Y.Khan  (01)  Khanpur  (01)  Liaquatpur  (01) | Notified | Done | Not deposited | - | * Assistant Commissioner Concerned is working as LAC of this project. Further process is underway for issuance of Notification either under the provisions of Section 5 or 17(4) & 6 |
| 9 | Higher Education Department  Acquisition of land for Construction of Associate College. | Higher Education Department | R.Y.Khan  (01) | Notified | Done | Not Deposited | - | * Assistant Commissioner Concerned is working as LAC of this project. Further process is underway for issuance of Notification either under the provisions of Section 5 and 17(4) & 6 subject to deposit of sufficient funds by the Acquiring Agency. |
| Liaquatpur  (2) | Notified | Done | Not Deposited | - |